## NIF
391 | 648962 | Run new conduit from panels to cleanroom, assemble clean room, install new breakers, wire, supports, mount (6) power supply units, connect FFU`s, lighting units, unplug existing lighting and zip tie cords to fixtures, anchor framework to floor. | Ready to work | 45432 | 45436 | Electrician
391 | 629573 | Run (approx. 400 feet) of conduit and communication wire from (391ACU14) to ALC for control upgrade activity. | Ready to work | 45432 | 45436 | Electrician
490 | 629280 | Equipment Label: 490ACSPH01-8P Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 45436 | 45436 | HVAC
490 | 629273 | Equipment Label: 490ACSPH02-9P Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 45436 | 45436 | HVAC

## By Bldg (hidden)
March 11, 2024
Attendees:
Facility | Work Order Number | Scope Description | Craft | Status | Target Start Date | Estimated Hours | % Complete | Must Have Date | Est. Complete Date | Meeting Notes
391
490, 482
493, 581, 681
162, 165, 298, 392
298 | 584217 | Annual Emergeny Lighting Inspection | Lighting
298 | 635593 | B298 rm#145,146- add new LED light over workbench and upgrade existing lights to LED in hallway in front of rm 146. Replace failing lighting relays, x-formers and switches as needed. | Lighting
298 | 591520 | PM Discovered Repair from 526909 298TLN01 Prep and paint foot pads of tank. The foot pads were rusted from the initial installation. | Painters
381, 481, 491, 3925
571, 583, 671, 3724

## Removed
Work Order | Description | Building/Equipment | MRC | Trade | Urgency Level | Work Type | Status | Activity | Bldg - Floor - Room | Budget Code | Date Created | Date Opened | Estimated Hours | FPOC/FM | Funding Type | Location | PFN | People Required | Requested End Date | Requested Start Date | Comments
584783 | NIF PAINT-RB113-Paint ends of optic table to match existing | 391 | NIF | ALL CRAFTS | 3 | Corrective Maintenance (Repair) | Ready to Work | 10 | 391-B-B113 |  | 2023-04-26 | 2023-04-26 12:57 | 0 | ROBISON2 | Client |  |  | 1 |  |  | Work order no longer needed and will be cancelled per FM during job walk
648094 | RM142-patch and paint holes in rm 142. - Report to Supervisor to modify activity, or if LOTO is needed. | RM142-patch and paint holes in rm 142. - Report to Supervisor to modify activity, or if LOTO is needed. | 298 | NIF | PAINTERS | Corrective Maintenance (Repair) | Ready to Work | SILVA203 | 3 | 24 | 47123 | 72870 |  | 20 | 2024-02-21 |  | 2024-02-21 |  | 2024-02-21 |  | Completed already per Ty
311603 | Retrofit T8 Fluorescent lights to LED. (estimated 32hrs/ 2 person) | Original Request: Retrofit T8 Fluorescent lights to LED. (estimated 36hrs/ 2 person) | 581 | NIF | LIGHTING | Corrective Maintenance (Repair) | Ready to Work | YEOMAN2 | 1 | 0 | 40542 | 91617 |  | 30 | 2019-01-24 |  | 2019-01-24 |  | 2019-01-24 |  | Completed already per Matt
311603 | meet with fM to clarify work | Original Request: Retrofit T8 Fluorescent lights to LED. (estimated 36hrs/ 2 person) | 581 | NIF | LIGHTING | Corrective Maintenance (Repair) | Ready to Work | YEOMAN2 | 1 | 0 | 40542 | 91617 |  | 20 | 2019-01-24 |  | 2019-01-24 |  | 2019-01-24 |  | Completed already per Matt
647427 | Paint TPS step brackets, paint 3ea of the attached drawings. Ref drawing 1012899549 and 1012895637. They will be getting painted in the paint shop. | Paint TPS step brackets, paint 3ea of the attached drawings. Ref drawing 1012899549 and 1012895637. They will be getting painted in the paint shop. | 581 | NIF | PAINTERS | Corrective Maintenance (Repair) | Ready to Work |  | 2 | 12 | 40542 | 91617 | Contact Matt Barbaris for details. | 20 | 2024-02-16 |  | 2024-02-16 |  | 2024-02-16 |  | Completed already per Matt
635444 | R1160 Lobby-Patch and paint to match existing color. To be completed by 1/5/2024. Report to Supervisor to modify activity, or if LOTO is needed. | 391 | 391 | NIF | PAINTERS | [15 empty] | Cancelled per Mark
635444 | R1160 Lobby-Patch and paint to match existing color. To be completed by 1/5/2024. Report to Supervisor to modify activity, or if LOTO is needed. | 391 | 391 | NIF | PAINTERS | [15 empty] | Cancelled per RI update
482 | 637028 | R1118 & R1313 -Replace failed lamps w/color matched bulbs, to include ballast, and lighting components. Office lighting out. Report to Supervisor to modify activity, or if complex LOTO is needed. | Ready to Work |  |  | 36 | [6 empty] | Pri 1 | [7 empty] | completed
298 | 651752 | Replace failed lamps w/color matched bulbs, to include ballast, and lighting components. R126,128. Report to Supervisor to modify activity, or if complex LOTO is needed. | Ready to Work |  |  | 5 | [5 empty] | 0 | Pri 1 | [7 empty] | completed
482 | 647880 | Patch and paint multiple rooms | Ready to work |  |  | 40 | [6 empty] | Carry over work. WO included multiple rooms. Stillworking on this scope creep added additional hours and rooms. Removed to break up into inddicd
490 | 561716 | Paint door & frame to room 1440 red to match the other doors in the hall. Note door shall remain white on the lab side in room 1440. | Ready to work |  |  | 16 | [6 empty] | Complete by EOD 4/8/24
482 | SR116507 | job require a job walk with Facility Management, job require additional discussion w/Bob Arthur to clarify work scope, boundary conditions, or area hazards |  |  |  | 0 | [6 empty] | Bob to cancel
581 | 594901 | B581 -NID HUT R2007 - Prep, Patch & Paint walls where there was previous core drilling. Report to Supervisor to modify activity, or if LOTO is needed. | Ready to work |  |  | 30 |  |  | client |  |  |  | Waiting on FM to approve