## NIF
391 | 648962 | Run new conduit from panels to cleanroom, assemble clean room, install new breakers, wire, supports, mount (6) power supply units, connect FFU`s, lighting units, unplug existing lighting and zip tie cords to fixtures, anchor framework to floor. | Ready to work | 2024-05-20 | 2024-05-24 | Electrician
391 | 629573 | Run (approx. 400 feet) of conduit and communication wire from (391ACU14) to ALC for control upgrade activity. | Ready to work | 2024-05-20 | 2024-05-24 | Electrician
490 | 629280 | Equipment Label: 490ACSPH01-8P Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 2024-05-24 | 2024-05-24 | HVAC
490 | 629273 | Equipment Label: 490ACSPH02-9P Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 2024-05-24 | 2024-05-24 | HVAC
490 | 629277 | Equipment Label: 490ACSPH03-X Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 2024-05-24 | 2024-05-24 | HVAC
490 | 629276 | Equipment Label: 490ACSPH04-X Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 2024-05-24 | 2024-05-24 | HVAC
490 | 629275 | Equipment Label: 490ACSPH05-X-P Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 2024-05-24 | 2024-05-24 | HVAC
490 | 629278 | Equipment Label: 490ACSPH06-10-X-P Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 2024-05-24 | 2024-05-24 | HVAC
490 | 629274 | Equipment Label: 490ACSPH07-X-P Task Plan: AC-32 AC-32-MW COMPUTER AC'S (CRACS) | Ready to Work | 2024-05-24 | 2024-05-24 | HVAC
490 | 521581 | Equipment Label: 490DDCP10 Task Plan: AC-97 AC-97 DDCP CONTROLLING CHILLERS & BOILERS BI-ENNIAL PM | Ready to Work | 2024-05-22 | 2024-05-22 | HVAC
490 | 522083 | Equipment Label: 490DDCP11 Task Plan: AC-97 AC-97 DDCP CONTROLLING CHILLERS & BOILERS BI-ENNIAL PM | Ready to Work | 2024-05-22 | 2024-05-22 | HVAC
490 | 632284 | Equipment Label: 490RCA01-10P Task Plan: AC-30 AC-30-26W-MW CONDENSING UNIT PM | Ready to Work | 2024-05-23 | 2024-05-23 | HVAC
490 | 632281 | Equipment Label: 490RCA02-8P Task Plan: AC-30 AC-30-26W-MW CONDENSING UNIT PM | Ready to Work | 2024-05-23 | 2024-05-23 | HVAC
490 | 632282 | Equipment Label: 490RCA03-9P Task Plan: AC-30 AC-30-26W-MW CONDENSING UNIT PM | Ready to Work | 2024-05-23 | 2024-05-23 | HVAC
490 | 630350 | Equipment Label: 490RCHSR01-1 Task Plan: AC-30 AC-30-26W-MW CONDENSING UNIT PM | Ready to Work | 2024-05-23 | 2024-05-23 | HVAC
490 | 630298 | Equipment Label: 490RCHSR02-1 Task Plan: AC-30 AC-30-26W-MW CONDENSING UNIT PM | Ready to Work | 2024-05-23 | 2024-05-23 | HVAC
490 | 630916 | Equipment Label: 490RCUA01 Task Plan: AC-30 AC-30-26W-MW CONDENSING UNIT PM | Ready to Work | 2024-05-23 | 2024-05-23 | HVAC
490 | 632283 | Equipment Label: 490RCUA05-1-A1 Task Plan: AC-30 AC-30-26W-MW CONDENSING UNIT PM | Ready to Work | 2024-05-23 | 2024-05-23 | HVAC
490 | 632280 | Equipment Label: 490RCUA06-1-1 Task Plan: AC-30 AC-30-26W-MW CONDENSING UNIT PM | Ready to Work | 2024-05-23 | 2024-05-23 | HVAC
490 | 665042 | 490ACU04-1 - Apply LOTO. Perform visual inspection, w/ photos, of all blower wheels. Provide photos to RI, FPOC for review. | Ready to Work | 2024-05-20 | 2024-05-20 | HVAC
490 | 665047 | 490ACU07-R(A) - Apply LOTO. Perform visual inspection, w/ photos, of all blower wheels. Provide photos to RI and FPOC for review. | Ready to Work | 2024-05-20 | 2024-05-20 | HVAC
571 | 595647 | Equipment Label: 571ACHPS31-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-20 | 2024-05-20 | HVAC
571 | 595649 | Equipment Label: 571ACHPS22-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-20 | 2024-05-20 | HVAC
571 | 595650 | Equipment Label: 571ACHPS16-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-20 | 2024-05-20 | HVAC
571 | 595722 | Equipment Label: 571ACHPS13-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-20 | 2024-05-20 | HVAC
571 | 595692 | Equipment Label: 571ACHPS09-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-20 | 2024-05-20 | HVAC
571 | 595653 | Equipment Label: 571ACHPS15-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-20 | 2024-05-20 | HVAC
571 | 595654 | Equipment Label: 571ACHPS27-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-20 | 2024-05-20 | HVAC
571 | 595691 | Equipment Label: 571ACHPS18-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-21 | 2024-05-21 | HVAC
571 | 595715 | Equipment Label: 571ACHPS10-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-21 | 2024-05-21 | HVAC
571 | 595626 | Equipment Label: 571ACHPS29-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-21 | 2024-05-21 | HVAC
571 | 595642 | Equipment Label: 571ACHPS01-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-21 | 2024-05-21 | HVAC
571 | 595687 | Equipment Label: 571ACHPS02-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-21 | 2024-05-21 | HVAC
571 | 595689 | Equipment Label: 571ACHPS36-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-21 | 2024-05-21 | HVAC
571 | 595714 | Equipment Label: 571ACHPS23-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-21 | 2024-05-21 | HVAC
571 | 595639 | Equipment Label: 571ACHPS08-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-22 | 2024-05-22 | HVAC
571 | 595686 | Equipment Label: 571ACHPS19-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-22 | 2024-05-22 | HVAC
571 | 595627 | Equipment Label: 571ACHPS34-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-22 | 2024-05-22 | HVAC
571 | 595628 | Equipment Label: 571ACHPS33-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-22 | 2024-05-22 | HVAC
571 | 595629 | Equipment Label: 571ACHPS03-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-22 | 2024-05-22 | HVAC
571 | 595631 | Equipment Label: 571ACHPS07-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-22 | 2024-05-22 | HVAC
571 | 595636 | Equipment Label: 571ACHPS06-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-22 | 2024-05-22 | HVAC
571 | 595685 | Equipment Label: 571ACS01 Task Plan: AC-03 AC-03 ACS PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-22 | 2024-05-22 | HVAC
571 | 595688 | Equipment Label: 571ACHPS32-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595707 | Equipment Label: 571ACHPS24-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595709 | Equipment Label: 571ACHPS17-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595716 | Equipment Label: 571ACHPS12-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595640 | Equipment Label: 571ACHPS26-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595641 | Equipment Label: 571ACHPS25-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595690 | Equipment Label: 571ACHPS30-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595646 | Equipment Label: 571ACHPS35-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595651 | Equipment Label: 571ACHPS20-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-23 | 2024-05-23 | HVAC
571 | 595652 | Equipment Label: 571ACHPS05-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-24 | 2024-05-24 | HVAC
571 | 595708 | Equipment Label: 571ACHPS28-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-24 | 2024-05-24 | HVAC
571 | 595710 | Equipment Label: 571ACHPS04-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-24 | 2024-05-24 | HVAC
571 | 595713 | Equipment Label: 571ACHPS21-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-24 | 2024-05-24 | HVAC
571 | 595717 | Equipment Label: 571ACHPS14-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-24 | 2024-05-24 | HVAC
571 | 595723 | Equipment Label: 571ACHPS11-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-24 | 2024-05-24 | HVAC
571 | 595907 | Equipment Label: 571ACHPS37-X Task Plan: AC-02 AC-02 HEAT PUMP PREVENTIVE MAINTENANCE | Ready To Work | 2024-05-24 | 2024-05-24 | HVAC
581 | 628518 | B581 - Switch yard 1 & 2 Ceiling Lights - Replace Linear fluorescent with LED type (~42 fixtures per SY. (84 total). Existing fixtures are 2'x2' linear fluorescent. | Ready to Work | 2024-05-21 | 2024-05-23 | Lighting
381 | 592570 | ANNUAL EMERGENCY LIGHTING INSPECTION PM | Ready to Work | 2024-05-20 | 2024-05-20 | Lighting
481 | 581290 | ANNUAL EMERGENCY LIGHTING INSPECTION PM | Ready to Work | 2024-05-20 | 2024-05-20 | Lighting
391 | 593428 | ANNUAL EMERGENCY LIGHTING INSPECTION PM | Ready to Work | 2024-05-20 | 2024-05-20 | Lighting
482 | 665882 | R1343A - Light above cubicle making a loud buzzing sound. Investigate and repair as needed. | Ready to Work | 2024-05-22 | 2024-05-22 | Lighting
482 | 665877 | R2005 - Supply room lights are almost all out. Replace FLOs/ballasts as needed. | Ready to Work | 2024-05-22 | 2024-05-22 | Lighting
298 | 665169 | Replace failed lamps w/color matched bulbs, to include ballast, and lighting components. RM185-asses and repair lights in room. Report to Supervisor to modify activity, or if complex LOTO is needed. | Ready to Work | 2024-05-23 | 2024-05-23 | Lighting
381 | 662028 | R1557 - Replace burnt out FLO's in lab and assess lights that are flickering | Ready to Work | 2024-05-23 | 2024-05-23 | Lighting
581 | 625275 | DLI CC - VISAR RM 2080 - Repair sheet rock affected from conduit install. Report to Supervisor to modify activity, or if LOTO is needed. | Ready to work | Fill in when available |  | Painting
381 | 620593 | B381 West Parking Lot Area - Re-paint Gov't parking and regular parking spaces | Ready to work | 2024-05-18 | 2024-05-18 | Painting
490 | 622512 | Patch and paint wall areas as needed. | Ready to work | 2024-05-20 | 2024-05-20 | Painting
490 | 622511 | Patch and paint wall areas as needed. | Ready to work | 2024-05-21 | 2024-05-21 | Painting
298 | 659534 | Paint crosswalks and painted 10mph signs on tenth st behind b298 for safety and pedestrians. Report to Supervisor to modify activity, or if LOTO is needed. | Ready to work | 2024-05-22 | 2024-05-22 | Painting
298 | 518327 | Patch and paint areas on wall from equipment anchor points. | Ready to work | 2024-05-23 | 2024-05-23 | Painting
581 | 594901 | B581 -NID HUT R2007 - Prep, Patch & Paint walls where there was previous core drilling. Report to Supervisor to modify activity, or if LOTO is needed.
381 | 559093 | Repair leak at union section of HHW supply pipe in mechanical room area near ACU07 (B381 R1422) Report to RI/Supervisor for additional activities and LOTO Validation if required. | Ready to Work
391 | 642318 | Outside of R1202A Repair broken Sanitary Sewer piping. Attached drawings define work. Confirm that work on P-100 is already completed and apply LOTO to slide valve to bypass sewer during P-200 work. | Ready to Work | 2024-05-20 |  | Plumbing
391 | 637325 | RB330-Build out B330 lab: Install various utilities including piping new fittings, valves, sink, piping for 2 city water supply lines 7 drops for house air. See Ray Williams for sink plumbing drawings. | Ready to Work | 2024-05-21 |  | Plumbing
391 | 663288 | R1228 Men's room sink on the right faucet leaks, assess and repair.as needed. | Ready to Work | 2024-05-22 | 2024-05-22 | Plumbing
581 | 662524 | RM 1028 Core toilet running Investigate and repair. Water has been turned off to toilet and it is posted out of order.(Craft will need escort to area) | Ready to Work | 2024-05-23 | 2024-05-23 | Plumbing

## By Bldg (hidden)
March 11, 2024
Attendees:
Facility | Work Order Number | Scope Description | Craft | Status | Target Start Date | Estimated Hours | % Complete | Must Have Date | Est. Complete Date | Meeting Notes
391
490, 482
493, 581, 681
162, 165, 298, 392
298 | 584217 | Annual Emergeny Lighting Inspection | Lighting
298 | 635593 | B298 rm#145,146- add new LED light over workbench and upgrade existing lights to LED in hallway in front of rm 146. Replace failing lighting relays, x-formers and switches as needed. | Lighting
298 | 591520 | PM Discovered Repair from 526909 298TLN01 Prep and paint foot pads of tank. The foot pads were rusted from the initial installation. | Painters
381, 481, 491, 3925
571, 583, 671, 3724

## Removed
Work Order | Description | Building/Equipment | MRC | Trade | Urgency Level | Work Type | Status | Activity | Bldg - Floor - Room | Budget Code | Date Created | Date Opened | Estimated Hours | FPOC/FM | Funding Type | Location | PFN | People Required | Requested End Date | Requested Start Date | Comments
584783 | NIF PAINT-RB113-Paint ends of optic table to match existing | 391 | NIF | ALL CRAFTS | 3 | Corrective Maintenance (Repair) | Ready to Work | 10 | 391-B-B113 |  | 2023-04-26 | 2023-04-26 12:57 | 0 | ROBISON2 | Client |  |  | 1 |  |  | Work order no longer needed and will be cancelled per FM during job walk
648094 | RM142-patch and paint holes in rm 142. - Report to Supervisor to modify activity, or if LOTO is needed. | RM142-patch and paint holes in rm 142. - Report to Supervisor to modify activity, or if LOTO is needed. | 298 | NIF | PAINTERS | Corrective Maintenance (Repair) | Ready to Work | SILVA203 | 3 | 24 | 47123 | 72870 |  | 20 | 2024-02-21 |  | 2024-02-21 |  | 2024-02-21 |  | Completed already per Ty
311603 | Retrofit T8 Fluorescent lights to LED. (estimated 32hrs/ 2 person) | Original Request: Retrofit T8 Fluorescent lights to LED. (estimated 36hrs/ 2 person) | 581 | NIF | LIGHTING | Corrective Maintenance (Repair) | Ready to Work | YEOMAN2 | 1 | 0 | 40542 | 91617 |  | 30 | 2019-01-24 |  | 2019-01-24 |  | 2019-01-24 |  | Completed already per Matt
311603 | meet with fM to clarify work | Original Request: Retrofit T8 Fluorescent lights to LED. (estimated 36hrs/ 2 person) | 581 | NIF | LIGHTING | Corrective Maintenance (Repair) | Ready to Work | YEOMAN2 | 1 | 0 | 40542 | 91617 |  | 20 | 2019-01-24 |  | 2019-01-24 |  | 2019-01-24 |  | Completed already per Matt
647427 | Paint TPS step brackets, paint 3ea of the attached drawings. Ref drawing 1012899549 and 1012895637. They will be getting painted in the paint shop. | Paint TPS step brackets, paint 3ea of the attached drawings. Ref drawing 1012899549 and 1012895637. They will be getting painted in the paint shop. | 581 | NIF | PAINTERS | Corrective Maintenance (Repair) | Ready to Work |  | 2 | 12 | 40542 | 91617 | Contact Matt Barbaris for details. | 20 | 2024-02-16 |  | 2024-02-16 |  | 2024-02-16 |  | Completed already per Matt
635444 | R1160 Lobby-Patch and paint to match existing color. To be completed by 1/5/2024. Report to Supervisor to modify activity, or if LOTO is needed. | 391 | 391 | NIF | PAINTERS | [15 empty] | Cancelled per Mark
635444 | R1160 Lobby-Patch and paint to match existing color. To be completed by 1/5/2024. Report to Supervisor to modify activity, or if LOTO is needed. | 391 | 391 | NIF | PAINTERS | [15 empty] | Cancelled per RI update
482 | 637028 | R1118 & R1313 -Replace failed lamps w/color matched bulbs, to include ballast, and lighting components. Office lighting out. Report to Supervisor to modify activity, or if complex LOTO is needed. | Ready to Work |  |  | 36 | [6 empty] | Pri 1 | [7 empty] | completed
298 | 651752 | Replace failed lamps w/color matched bulbs, to include ballast, and lighting components. R126,128. Report to Supervisor to modify activity, or if complex LOTO is needed. | Ready to Work |  |  | 5 | [5 empty] | 0 | Pri 1 | [7 empty] | completed
482 | 647880 | Patch and paint multiple rooms | Ready to work |  |  | 40 | [6 empty] | Carry over work. WO included multiple rooms. Stillworking on this scope creep added additional hours and rooms. Removed to break up into inddicd
490 | 561716 | Paint door & frame to room 1440 red to match the other doors in the hall. Note door shall remain white on the lab side in room 1440. | Ready to work |  |  | 16 | [6 empty] | Complete by EOD 4/8/24
482 | SR116507 | job require a job walk with Facility Management, job require additional discussion w/Bob Arthur to clarify work scope, boundary conditions, or area hazards |  |  |  | 0 | [6 empty] | Bob to cancel
581 | 594901 | B581 -NID HUT R2007 - Prep, Patch & Paint walls where there was previous core drilling. Report to Supervisor to modify activity, or if LOTO is needed. | Ready to work |  |  | 30 |  |  | client |  |  |  | Waiting on FM to approve